## Project Planner
Project Planner
[7 empty] | Period Highlight: | 7 |  |  | Plan Duration |  |  |  |  | Actual Start |  | % Complete
ACTIVITY | COMPONENTS | PRIMARY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE |  |  |  | Actual (beyond plan) | [5 empty] | % Complete (beyond plan)
Day
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Problem Statement | - Research and Formulating | All | 1 | 2 | 1 | 2 | 100%
EDA | - Data exploration and Insights | Lucus, Dale | 2 | 4 | 2 | 4 | 100%
Feature Engineering | - Transform Data into features for modeling based on EDA | Dale, Lucus | 2 | 4 | 2 | 4 | 100%
Pre - Modeling | - Create Scoring and Model Functions | Dave | 2 | 4 | 2 | 4 | 100%
Modeling | - Input preprocessed Data into models, and hypertune the parameters | Lucus, Dave | 6 | 2 | 6 | 2 | 100%
Cost Benefit Analysis | - Analyse on the Cost vs Benefit on Spraying | Dale | 6 | 2 | 6 | 2 | 100%
Conclusion and Recommendation | - Conclude and recommend on the findings from the models | Dave | 7 | 1 | 7 | 1 | 100%
README and Presentation Slides | - Compile all relevant findings | All | 7 | 1 | 7 | 1 | 100%